## Slide 1: Critical Path Method
Example selection:田沛熙
PowERPOINT:周正宜 范炳健 张文博
REPORT：董自经

## Slide 2: THREE PARTS
1.Example Introduction
2.Table of events
3.CPM
4.Gantt chart

## Slide 3: English Language Culture Festival
Welcome to our upcoming English Cultural Festival!
Aim:
Celebrate the diversity and richness of the English language
Provide a platform to showcase the cultural characteristics of different countries
Inspire participants to be passionate about learning English
Promote understanding and respect for different cultures.
PART 1 :EXAMPLE INTRODUCTION

## Slide 4
PART 2 :TABLE OF EVENTS
Determine the theme
Organize meetings
Determine the activities list
Recruit volunteers
Arrange space and equipment
Publicize events
Prepare materials and equipment
Hold the festival
1
1
2
3
4
1
2
1
4.5.7
6
3
3
0
2
1
0

## Slide 5: Formulation
EF=ES+D
LS=LF-D
ES=max(pre_activities.EF)
(先决活动的最早结束中的最大值)
LF=min(sub_activities.LS)
(后续活动的最晚开始中的最小值)

## Slide 6
Activity name |  | 
ES | D | EF
ST |  | ST
LS | D | LF
PART 3:CPM
Determine the theme
Recruit volunteers
Prepare materials
Publicize events
Organize meetings
Arrange space and equipment
Determine activities list
Hold the festival
0
0
0
0
0
0
0
0
0
0
0
0
1
1
1
1
1
1
1
1
1
1
1
1
0
2
2
2
2
2
2
2
2
2
2
2
2
4
4
4
4
4
4
4
4
6
3
6
6
1
5
5
8
8
8
8
8
8
6
6
6
5
5
1
1
1
7
7
1
8
9
9
EF=ES+D
LS=LF-D
ES=max(pre_activities.EF)
LF=min(sub_activities.LS)

## Slide 7
Gantt Chart
PART 4：Gantt Chart

## Slide 8: Thanks for listening
Group 1